## Sprint
|  |  |  | Week #1 (10 hrs / week) | [6 empty] | Week #2 (10 hrs / week)
Backlog Item | Task | Task Owner | Initial Estimate (Total Sprint Hours = 50 x 2) | D1 | D2 | D3 | D4 | D5 | D6 | D7 | D8 | D9 | D10 | D11 | D11
|  |  |  | 2019-11-11 | 2019-11-12 | 2019-11-13 | 2019-11-14 | 2019-11-15 | 2019-11-16 | 2019-11-17 | 2019-11-18 | 2019-11-19 | 2019-11-20 | 2019-11-21 | 2019-11-22
|  |  |  | 100 | 90 | 80 | 70 | 60 | 50 | 45 | 35 | 25 | 15 | 5 | 0 | Ideal Burndown
|  |  | 100 | 94 | 88 | 83 | 76 | 67 | 56 | 51 | 41 | 29 | 15 | 2 | 0 | Remaining Hrs (Total)
Requirement Gathering and Designing | Design Requirement | Harshada | 5 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Collect audio for ad video game | Mayura | 10 | 10 | 9 | 9 | 8 | 5 | 2 | 2 | 2 | 2 | 2 | 1 | 0
| Design ad video | Harshada | 10 | 10 | 9 | 8 | 6 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0
| Collect images for ad video and game | Sonia | 10 | 8 | 7 | 7 | 5 | 5 | 3 | 3 | 2 | 2 | 1 | 0 | 0
| Track progress and miscellenious support | Sheethal | 5 | 5 | 3 | 3 | 3 | 3 | 2 | 2 | 2 | 2 | 1 | 0 | 0
| Set up git folders | Prathamesh | 5 | 3 | 3 | 3 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
Implementation | Decide classes and interfaces required for game | Harshada | 5 | 5 | 4 | 3 | 3 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0
| Work on alien and destruction implementation | Mayura | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 8 | 5 | 3 | 1 | 0
| Work on explosives and level implementation | Prathamesh | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 7 | 4 | 2 | 0 | 0
| Work on weapons and health implementation | Sonia | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 8 | 6 | 1 | 0 | 0
| Work on scores implementation and main page | Sheethal | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 2 | 2 | 0 | 0
| Work on Bazooka(Savior) implementation | Harshada | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 3 | 3 | 2 | 0 | 0
| Design Pattern Notes | Prathamesh | 5 | 5 | 5 | 5 | 5 | 3 | 2 | 2 | 2 | 1 | 1 | 0 | 0
| UML Diagrams | Harshada | 5 | 5 | 5 | 5 | 5 | 5 | 3 | 2 | 2 | 2 | 0 | 0 | 0
Team:
Harshada | 10 hours / Week
Mayura | 10 hours / Week
Prathamesh | 10 hours / Week
Sonia | 10 hours / Week
Sheethal | 10 hours / Week
Total Available Hours During Sprint: | 100