## Sprint
|  |  |  | Week #1 (10 hrs / week) | [6 empty] | Week #2 (10 hrs / week)
Backlog Item | Task | Task Owner | Initial Estimate (Total Sprint Hours = 10 x 5) | D1 | D2 | D3 | D4 | D5 | D6 | D7 | D8 | D9 | D10 | D11
|  |  |  | 2014-11-10 | 2014-11-11 | 2014-11-13 | 2014-11-14 | 2014-11-15 | 2014-11-16 | 2014-11-17 | 2014-11-18 | 2014-11-19 | 2014-11-20 | 2014-11-21
|  |  |  | 50 | 45 | 40 | 35 | 30 | 25 | 20 | 15 | 10 | 5 | 0 | Ideal Burndown
|  |  | 100 | 47 | 44 | 38 | 34 | 35 | 26 | 19 | 12 | 6 | 2 | 0 | Remaining Hrs (Total)
Requirement Gathering and Designing | Design Requirement | Harshada | 5 | 5 | 5 | 0 | 0 | 4 | 5 | 4 | 1 | 0 | 0 | 0
| Collect audio for ad video game | Mayura | 10 | 10 | 9 | 9 | 8 | 10 | 5 | 5 | 4 | 2 | 0 | 0
| Design ad video | Harshada | 10 | 10 | 9 | 8 | 6 | 2 | 1 | 0 | 0 | 0 | 0 | 0
| Collect images for ad video and game | Sonia | 10 | 8 | 8 | 9 | 10 | 10 | 8 | 6 | 3 | 2 | 1 | 0
| Track progress and miscellenious support | Sheethal | 5 | 4 | 3 | 4 | 3 | 3 | 4 | 3 | 3 | 2 | 1 | 0
| Set up git folders | Prathamesh | 5 | 5 | 5 | 4 | 3 | 3 | 1 | 0 | 0 | 0 | 0 | 0
Implementation | Decide classes and interfaces required for game | Harshada | 5 | 5 | 5 | 4 | 4 | 3 | 2 | 1 | 1 | 0 | 0 | 0
| Work on alien and destruction implementation | Mayura | 10 | 0 | 6 | 9 | 9 | 2 | 10 | 10 | 8 | 6 | 4 | 3
| Work on explosives and score implementation | Prathamesh | 10 | 0 | 7 | 9 | 10 | 10 | 10 | 10 | 10 | 6 | 2 | 0
| Work on weapons and health implementation | Sonia | 10 | 0 | 6 | 9 | 10 | 10 | 10 | 10 | 10 | 10 | 1 | 0
| Work on levels implementation and main page | Sheethal | 5 | 0 | 0 | 1 | 3 | 5 | 1 | 5 | 5 | 5 | 2 | 0
| Work on Bazooka(Savior) implementation | Harshada | 5 | 0 | 0 | 1 | 5 | 5 | 5 | 5 | 5 | 5 | 2 | 0
| UML Diagrams | Prathamesh | 5 | 0 | 0 | 1 | 4 | 2 | 5 | 5 | 5 | 1 | 1 | 0
| Design Pattern Notes | Harshada | 5 | 0 | 0 | 1 | 0 | 0 | 5 | 5 | 5 | 2 | 0 | 0
Team:
Harshada | 10 hours / Week
Mayura | 10 hours / Week
Prathamesh | 10 hours / Week
Sonia | 10 hours / Week
Sheethal | 10 hours / Week
Total Available Hours During Sprint: | 100